## Sheet1
FPIN HDA Projection Tool
Date submitted to FPIN | 2017-10-31 | Instructions:
Author team will receive technical check feedback from FPIN | 2017-11-07 | 1. Type in the date that you submit or plan to submit your first draft
Author needs to submit any requests from technical check back to FPIN by this date | 2017-11-14 | 2. Review the dates that populate. The dates in red are dates when the author team needs to be prepared to submit something back.
Peer Review should be complete by this date. Author team will receive an email notication when it is complete. If not, the Corresponding Author should inquire for an update. | 2018-03-14 | 3. It is important to note that the dates are based on worst case scenerio for times when our peer reviewers and editor capacity is low. However, it is also based on there being NO due date extensions and everyone in the process keeping to their deadlines at every point in the process. Therefore, when you balance all of these factors - this timeline is generally accurate.
Deputy Editor should complete the first review of the manuscript by this date | 2018-06-20 | 4. To get the most use out of this tool, you can type in the actual dates that your manuscript meets these milestones and it will still populate the dates below to give you an updated expected publication date.
Author should be prepared to submit revisions back to the Deputy Editor | 2018-07-04 | 5. We will periodically update this tool with the most current timelines and wait times so be sure that the tool accurately reflects the state of things in the project
Deputy Editor should complete the second review of the manuscript by this date | 2018-07-18
Author should be prepared to submit revisions back to the Deputy Editor | 2018-08-01
Deputy Editor should complete the third review of the manuscript by this date | 2018-08-15
Author should be prepared to submit revisions back to the Deputy Editor | 2018-08-29
HelpDesk Answers EIC will review the manuscript by this date and provide feedback to the Deputy Editor | 2018-09-12
Deputy Editor will review EIC feedback and submit revision requests and may submit additional revision requests to the author team | 2018-09-26
Author should be prepared to submit revisions back to the Deputy Editor | 2018-10-10
Journal Editor-in-Chief and/or production team may request final edits before approving for publication | 2019-02-07
Author team should be prepared to submit revisions back to the Journal production team within 48 hours | 2019-02-09
Author Team should expect to see their HelpDesk Answer published in a journal | 2019-06-09
Updated Dec 14, 2017